## Deliverable Tracker
DELIVERABLE TRACKER — Services Leadership Team
ID | Initiative | Deliverable | Owner | Team | Due Date | Status | Days Aging | Escalation Notes
D-001 | Q2 Planning | Draft Q2 OKRs for Services org | J. Martinez | Strategy | 2026-03-25 | In Progress | —
D-002 | Q2 Planning | Finalize headcount plan | R. Chen | People Ops | 2026-03-28 | Not Started | — | Waiting on Finance approval
D-003 | Vendor Consolidation | Vendor spend analysis deck | S. Patel | Procurement | 2026-03-18 | Overdue | 5 | Escalated to VP 3/19
D-004 | Customer Onboarding | Revised onboarding playbook v2 | M. Williams | CX | 2026-03-22 | Complete | —
D-005 | Eng Reliability | SLA dashboard for leadership review | A. Kim | Engineering | 2026-04-01 | In Progress | —
D-006 | Q2 Planning | Budget reforecast submission | T. Johnson | Finance | 2026-03-20 | At Risk | 3 | Missing inputs from 2 teams
D-007 | Customer Onboarding | Partner integration requirements doc | L. Brown | Partnerships | 2026-04-05 | Not Started | —
D-008 | Vendor Consolidation | Contract renegotiation tracker | S. Patel | Procurement | 2026-04-10 | In Progress | —
D-009 | Eng Reliability | Incident retrospective summary Q1 | A. Kim | Engineering | 2026-03-21 | Complete | —
D-010 | Q2 Planning | Cross-functional dependency map | J. Martinez | Strategy | 2026-03-30 | In Progress | —
STATUS SUMMARY
Total Deliverables | 10
Complete | 2
In Progress | 4
At Risk | 1
Overdue | 1
Not Started | 2
Formulas:
Days Aging = IF([Status]="Complete","—",IF([Due Date]<TODAY(),TODAY()-[Due Date],"—"))

## Weekly Leadership Meeting
WEEKLY LEADERSHIP MEETING — Agenda & Action Items
Meeting Cadence: Every Monday 10:00–11:00 AM ET |  |  | Facilitator: [Operations Analyst]
# | Agenda Item | Presenter | Time (min) | Discussion Notes | Action Item | Owner / Due
1 | Opening: Review last week's action items | Ops Analyst | 5 | Walk through tracker — flag overdue items | Update status on 3 overdue items | S. Patel / 3/25
2 | Q2 Planning: OKR alignment check | J. Martinez | 15 | Review draft OKRs by team; flag misalignment | Finalize OKRs and circulate for comment | J. Martinez / 3/27
3 | Vendor Consolidation: Spend analysis review | S. Patel | 10 | Present top 5 vendor spend areas | Schedule deep-dive with Finance | S. Patel / 3/28
4 | Eng Reliability: Q1 incident recap | A. Kim | 10 | Summarize Q1 incidents and action plan | Share retrospective doc with leadership | A. Kim / 3/26
5 | Customer Onboarding: Playbook v2 sign-off | M. Williams | 10 | Final review before rollout | Distribute to CX team for training | M. Williams / 3/28
6 | Closing: New action items & next week preview | Ops Analyst | 5 | Recap new action items; confirm next agenda | Send meeting notes within 2 hours | Ops Analyst / 3/24
MEETING PREP CHECKLIST (Ops Analyst completes before each meeting)
☐ Pull latest deliverable tracker status — flag overdue and at-risk items
☐ Confirm agenda with each presenter 24 hours before meeting
☐ Pre-read materials distributed to attendees by Friday EOD
☐ Reserve conference room / confirm video link
☐ Prepare 1-page status summary slide for leadership
☐ Send meeting notes + updated action items within 2 hours post-meeting

## Business Review Calendar
BUSINESS REVIEW CALENDAR — Q2 2026
Date | Review Type | Focus Area | Presenter(s) | Prep Owner | Prep Deadline | Materials Status | Notes
2026-04-01 | Monthly Business Review | March performance + Q1 close | VP Services + Leads | Ops Analyst | 2026-03-27 | In Progress | Deck template sent 3/20
2026-04-08 | Sprint Review | Engineering sprint 12 demo | A. Kim | A. Kim | 2026-04-06 | Not Started
2026-04-15 | QBR Prep | Q1 QBR dry run with leadership | All Leads | Ops Analyst | 2026-04-10 | Not Started | External QBR on 4/22
2026-04-22 | Quarterly Business Review | Q1 results + Q2 outlook (external) | SVP Services | Ops Analyst | 2026-04-17 | Not Started | Board-level audience
2026-05-01 | Monthly Business Review | April performance recap | VP Services + Leads | Ops Analyst | 2026-04-28 | Not Started
2026-05-13 | Sprint Review | Engineering sprint 14 demo | A. Kim | A. Kim | 2026-05-11 | Not Started
2026-05-20 | Ops Excellence Review | Process improvement pipeline | Ops Analyst | Ops Analyst | 2026-05-15 | Not Started | New cadence starting Q2
2026-06-01 | Monthly Business Review | May performance recap | VP Services + Leads | Ops Analyst | 2026-05-28 | Not Started
2026-06-15 | Mid-Year Planning | H2 planning kickoff | SVP Services | Ops Analyst | 2026-06-10 | Not Started | Align with Finance timeline

## Dashboard
OPERATIONS DASHBOARD — Weekly Snapshot
Week of: March 23, 2026 |  |  | Prepared by: Sai Tarun Reddy
KEY METRICS |  |  | HEALTH INDICATORS
Total Open Deliverables | 10 |  | On-Time Delivery Rate | 0.2
Overdue Items | 1 |  | At-Risk Items | 1
Meetings This Week | 3 |  | Upcoming Business Reviews (30 days) | 2
OPEN ITEMS BY TEAM
Team | Open Items
Strategy | 2
People Ops | 1
Procurement | 2
CX | 0
Engineering | 1
Finance | 1
Partnerships | 1
ESCALATION LOG
Date | Item | Owner | Escalated To | Resolution
3/19 | Vendor spend analysis deck (D-003) | S. Patel | VP Procurement | Deadline extended to 3/25
3/20 | Budget reforecast inputs (D-006) | T. Johnson | CFO Office | Pending — follow up 3/24

## How To Use
HOW TO USE THIS TRACKER
This tracker is designed for an Operations Analyst supporting a Services Leadership Team.
It provides a single source of truth for deliverables, meetings, business reviews, and escalations.
TAB 1: DELIVERABLE TRACKER
• Add new deliverables as they are assigned. Update status weekly (or more often).
• "Days Aging" auto-calculates for overdue items. Use this to flag items in leadership meetings.
• Status options: Complete, In Progress, At Risk, Overdue, Not Started.
• Add escalation notes for anything flagged to VP or above.
TAB 2: WEEKLY LEADERSHIP MEETING
• Update the agenda each Friday before the Monday meeting.
• Use the prep checklist to ensure nothing is missed.
• Action items from the meeting should flow into the Deliverable Tracker (Tab 1).
TAB 3: BUSINESS REVIEW CALENDAR
• Maintain a rolling 90-day view of all business reviews.
• Track prep deadlines and materials status so nothing is last-minute.
TAB 4: DASHBOARD
• This is your weekly snapshot for leadership. Update every Monday morning.
• KPI formulas pull directly from the Deliverable Tracker — keep that tab current.
• The Escalation Log tracks items that required VP+ attention.
TAB 5: HOW TO USE (this tab)
• Share this tab with your manager on day one to show your operational approach.
Prepared by: Sai Tarun Reddy ¦ saitarunreddymittapalli@gmail.com ¦ 401-239-7925
GitHub: github.com/saitarunreddymittapalli-design/provider-ops-qa-portfolio